## README
AnovaCloud — Agentic AI Deployment Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Agent architecture decision matrix
Score per use case. Most organizations should start at the copilot tier and earn autonomy with eval evidence.
Criterion | Weight (1–5) | Single-agent assistant (rating 1–5) | Multi-agent workflow (rating 1–5) | Human-in-the-loop copilot (rating 1–5) | Defer / strengthen foundations (rating 1–5) | Guidance note
Task decomposability | 4 | 3 | 5 | 4 | 1 | Multi-step tasks with clear subtasks favor multi-agent; fuzzy tasks favor copilot.
Error tolerance | 5 | 2 | 2 | 5 | 1 | Low error tolerance demands the copilot's human gate.
Tool/API maturity | 5 | 4 | 3 | 4 | 1 | Immature tooling: defer or copilot only.
Eval readiness | 5 | 3 | 2 | 4 | 1 | No golden task set → no autonomous agents.
Latency sensitivity | 3 | 5 | 2 | 4 | 1 | Multi-agent chains add latency; real-time favors single-agent.
Cost per task budget | 3 | 4 | 2 | 4 | 1 | Multi-agent multiplies token spend; model the unit economics.
Auditability needs | 4 | 3 | 3 | 5 | 1 | Regulated actions need the copilot's explicit approvals.
Team ML-ops maturity | 4 | 3 | 2 | 4 | 1 | Multi-agent systems need serious eval/ops muscle.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
Agentic AI Deployment Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Frame | Select & score pilot use case | Product + architect | 2 weeks | Scored use case, blast-radius doc | Not started
| Write success criterion | Business owner |  | One-sentence acceptance criterion | Not started
| Inventory tools & data | Engineering |  | Tool/data inventory with gaps | Not started
| Assign autonomy tier | Architect |  | Tier decision with rationale | Not started
Phase 2 · Build the harness | Build golden task set | Domain expert + eng | 3–4 weeks | ≥50 graded tasks | Not started
| Stand up eval harness | ML engineer |  | Automated eval runs | Not started
| Harden tool contracts | Engineering |  | Versioned tool schemas | Not started
| Implement guardrails | Security + eng |  | Injection/PII/permission controls | Not started
Phase 3 · Sandbox pilot | Agent v1 in sandbox | Engineering | 3–4 weeks | Working agent on staging systems | Not started
| Eval-gated iteration | ML engineer |  | Eval trend: improving, no regressions | Not started
| Red-team pass | Security |  | Findings remediated | Not started
| Approval workflow build | Product + eng |  | Human gates in the path | Not started
Phase 4 · Limited production | Internal/limited rollout | Product | 4–6 weeks | Real traffic, human approval on risky actions | Not started
| Tracing & cost instrumentation | Platform |  | Per-run traces, cost dashboards | Not started
| Incident drill | Ops |  | Runbook executed, timings recorded | Not started
| Gate review: expand or hold | Architect + owner |  | Written gate decision | Not started
Phase 5 · Scale & govern | Expand autonomy per evidence | Architect | ongoing | Tier promotions tied to eval data | Not started
| Continuous eval & drift watch | ML engineer |  | Eval dashboard, drift alerts | Not started
| Cost optimization | Engineering |  | Cost-per-task trending down | Not started
| Portfolio review | Leadership |  | Which use cases graduate, which retire | Not started

## Validation Plan
Agentic AI Deployment Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Task effectiveness | Golden-set pass rate | Run full golden set on the release candidate | ≥ agreed threshold (e.g., 90%), no critical-task failures | Pending
| Tool-use correctness | Grade tool selection + arguments per task | ≥95% correct tool calls on golden set | Pending
| Recovery behavior | Inject tool failures/timeouts in sandbox | Agent recovers or escalates gracefully in ≥95% of cases | Pending
Safety | Prompt-injection suite | Run adversarial prompt set | Zero policy violations; all blocked or escalated | Pending
| Permission boundary test | Attempt out-of-scope actions | All denied and logged | Pending
| PII leakage test | Tasks touching sensitive data | Zero PII in traces/logs beyond policy | Pending
Reliability | Loop/timeout behavior | Tasks designed to trap agents in loops | Agent terminates within step/latency budget 100% | Pending
| Idempotency check | Replay mutating tasks | No duplicate side effects on retry | Pending
| Degraded-model fallback | Run on weaker/cheaper model | Graceful degradation; escalates instead of guessing | Pending
Economics | Cost per task | Measure tokens + tool cost per golden task | Within budget; p99 cost bounded | Pending
| Latency SLO | p95 task latency on golden set | Within product SLO | Pending
| Human-effort delta | Compare human time with/without agent on pilot | Net positive including review/override time | Pending
Operations | Trace completeness | Sample production traces | 100% of runs fully traceable | Pending
| Approval enforcement | Attempt to bypass approval gate | Bypass impossible without code change + review | Pending
| Kill-switch drill | Trigger spend/behavior anomaly | Agent halted within 60 seconds, alert fired | Pending