## README
AnovaCloud — AI Governance & Risk Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Governance operating-model decision matrix
There is no universally right model — only the one your organization will actually follow. Score honestly.
Criterion | Weight (1–5) | Centralized AI office (rating 1–5) | Federated (embedded) (rating 1–5) | Platform-embedded controls (rating 1–5) | Defer / ad-hoc (rating 1–5) | Guidance note
Decision speed | 4 | 2 | 4 | 5 | 5 | Centralized gates slow; embedded controls scale.
Consistency of controls | 5 | 5 | 2 | 4 | 1 | Federated models drift without strong standards.
Risk appetite fit | 5 | 5 | 3 | 4 | 1 | Low appetite needs real gates, not guidance.
Org change capacity | 4 | 2 | 3 | 4 | 5 | New central offices need sponsorship and hiring.
Engineering culture fit | 4 | 2 | 4 | 5 | 3 | Platform-embedded suits product-led orgs.
Audit defensibility | 5 | 5 | 3 | 4 | 1 | Regulators want evidence; ad-hoc has none.
Cost to operate | 3 | 2 | 3 | 4 | 5 | Central offices are expensive; embedded is efficient at scale.
Scalability with AI portfolio | 4 | 3 | 3 | 5 | 1 | Portfolios >20 systems need embedded or federated.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
AI Governance & Risk Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Discover | Build the AI inventory | AI program lead | 3–4 weeks | AI register v1 | Not started
| Draft risk-tiering model | Risk + legal |  | Tier definitions | Not started
| Tier all systems | Owners + risk |  | Tiered inventory | Not started
| Regulatory mapping | Legal/compliance |  | Obligation-to-control map | Not started
Phase 2 · Design | Design tiered control matrix | Risk + eng | 3–4 weeks | Control matrix | Not started
| Choose operating model | Leadership |  | Model decision + charter | Not started
| Draft policies & gates | Legal + risk |  | Policy pack v1 | Not started
| Define incident runbook | Security + risk |  | Incident runbook | Not started
Phase 3 · Pilot controls | Pilot gates on 2–3 high-risk systems | Owners | 4–6 weeks | Gate evidence packs | Not started
| Stand up monitoring | Platform |  | Monitoring specs live | Not started
| Train owners & approvers | AI office |  | Training records | Not started
| Board reporting template | AI owner |  | First board report | Not started
Phase 4 · Roll out | Roll out to all tiers | AI office | 6–8 weeks | Full coverage | Not started
| Procurement/intake hooks | Procurement + eng |  | Intake gate live | Not started
| Vendor diligence backlog | Risk |  | Vendor assessments filed | Not started
| First incident drill | Security |  | Drill record | Not started
Phase 5 · Assure | Quarterly re-tiering | AI office | ongoing | Updated tiers | Not started
| Control effectiveness review | Risk/audit |  | Review findings | Not started
| Annual program review | Leadership |  | Program health report | Not started
| Regulatory watch | Legal |  | Obligation updates | Not started

## Validation Plan
AI Governance & Risk Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Inventory integrity | Register completeness spot-check | Sample business units for unregistered AI | Zero material unregistered systems found | Pending
| Tiering accuracy | Independent re-tiering of 5 systems | Agreement on 4 of 5; disputes resolved | Pending
| Intake gate test | Submit a mock new-AI request | Caught and routed correctly | Pending
Control effectiveness | Gate enforcement | Attempt high-risk launch without sign-off (tabletop) | Blocked by process; evidence required | Pending
| Data-rights audit | Trace 3 systems' training data rights | Rights documented and valid for all 3 | Pending
| Vendor diligence | Review 3 vendor AI files | DPA, security review, exit plan on file | Pending
Testing rigor | Eval evidence | Inspect eval packs for high-risk systems | Metrics, thresholds, and results filed | Pending
| Red-team coverage | List high-risk systems vs. red-team dates | 100% red-teamed within policy window | Pending
| Monitoring live | Trigger a monitored condition in staging | Alert fires; runbook followed | Pending
Incident readiness | Tabletop exercise | Run AI incident scenario with responders | Roles, comms, and kill-switch steps executed | Pending
| Kill-switch drill | Halt a staging AI system | Halted within target time; rollback verified | Pending
| Rights request | Process a mock explanation/appeal request | Completed within policy SLA | Pending
Reporting | Board report review | Inspect last two AI risk reports | Accurate, tiered, with decisions requested | Pending
| Regulatory mapping currency | Check mapping against latest obligations | Current; gaps owned and dated | Pending
| Audit trail | Pull full evidence pack for one high-risk system | Complete chain: inventory → tier → tests → approval → monitoring | Pending