## README
AnovaCloud — AI-Ready Workforce Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Talent strategy decision matrix
Score per critical gap. The right answer varies by gap: upskill your data engineers on RAG, hire your eval lead, partner for the first agent build.
Criterion | Weight (1–5) | Upskill in place (rating 1–5) | Hire AI-native talent (rating 1–5) | Blend (upskill + hire) (rating 1–5) | Partner / managed team (rating 1–5) | Guidance note
Time to capability | 5 | 2 | 3 | 3 | 5 | Partnering is fastest; upskilling takes quarters.
Gap depth | 5 | 2 | 5 | 4 | 4 | Deep novel gaps (evals, agents) favor hire/partner.
Knowledge retention need | 4 | 5 | 4 | 5 | 2 | Partnering leaks knowledge unless KT is contracted.
Cost over 2 years | 3 | 5 | 3 | 3 | 2 | Upskilling is cheapest if retention holds.
Cultural fit & morale | 4 | 5 | 3 | 4 | 3 | Upskilling signals investment; pure hiring can demoralize.
Hiring market reality | 4 | 5 | 2 | 3 | 4 | Scarce roles take 6+ months to hire — price the delay.
Strategic differentiation | 4 | 4 | 5 | 5 | 2 | Core differentiators should be built in-house eventually.
Risk of getting it wrong | 4 | 3 | 3 | 4 | 5 | Partners de-risk first attempts with contractual accountability.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
AI-Ready Workforce Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Days 1–14 · Baseline | Run skills baseline | Eng leadership + L&D | 2 weeks | Fluency map | Not started
| Map role impacts | Leadership |  | Role-impact map | Not started
| Prioritize gaps | Leadership |  | Top-5 gaps with owners | Not started
| Choose talent strategy per gap | Leadership |  | Matrix decisions, written | Not started
Days 15–45 · Enable | Launch role-segmented paths | L&D + champions | 4–5 weeks | Paths live | Not started
| Stand up sandboxes | Platform |  | Guardrailed sandboxes | Not started
| Champion-led build sprints | Champions |  | First artifacts shipped | Not started
| Policy & review process | Security + L&D |  | Attested policy, live review | Not started
Days 46–75 · Ship | Cohort ships pilot builds | Teams | 4–5 weeks | Shipped internal AI tools | Not started
| Demo cadence | L&D |  | Demos recorded to playbook | Not started
| Hiring loops calibrated | Hiring managers |  | AI interview rubrics | Not started
| Partner KT (if any) | Partner + leads |  | KT evidence pack | Not started
Days 76–90 · Measure | Re-run skills baseline | L&D | 2 weeks | Skill deltas reported | Not started
| Artifact review | Champions |  | Quality assessment | Not started
| Retention check | HR + leadership |  | Retention actions | Not started
| Next-90 plan | Leadership |  | Sustained enablement plan | Not started
Beyond 90 · Sustain | Quarterly skill reviews | L&D | ongoing | Review log | Not started
| Playbook contributions | All |  | Compounding internal knowledge | Not started
| Hiring pipeline | Talent |  | AI roles filled per plan | Not started
| Advanced tracks | Champions |  | Evals/agents deep tracks | Not started

## Validation Plan
AI-Ready Workforce Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Skill evidence | Artifact review | Champions grade shipped builds | ≥80% meet the quality bar | Pending
| Baseline delta | Re-run baseline assessment | Targeted gaps improved ≥1 maturity level | Pending
| Explain-it test | Sample interviews on core concepts | ≥80% explain correctly | Pending
Behavior change | Tool adoption | Approved-stack usage metrics | Active weekly use by ≥70% of cohort | Pending
| AI in SDLC | PRs showing AI-assisted dev | Normalized: present in majority of teams | Pending
| Playbook contributions | Contributions per quarter | Growing; not just champions contributing | Pending
Business impact | Cycle-time delta | Compare delivery metrics pre/post | Improvement with quality held constant | Pending
| Pilot business outcomes | Pilot build success criteria | Met per the written criteria | Pending
| Incident rate | AI-related incidents/near-misses | No increase; near-misses caught by review | Pending
Governance | Policy attestation | Attestation records | 100% of AI builders attested | Pending
| Review cycle time | New-use review durations | Median <1 week | Pending
| Shadow-AI check | Survey + tool logs | Unapproved tool use trending down | Pending
Talent | Hiring progress | Must-hire roles vs. plan | On track or partner coverage in place | Pending
| Retention | Upskilled cohort attrition | At or below org baseline | Pending
| KT verification | Partner knowledge transfer | Demos + docs + paired work evidenced | Pending