## README
AnovaCloud — Cloud Migration Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
6R disposition decision matrix
Score each application 1–5 per criterion per disposition. The disposition with the highest weighted total is the recommendation — document overrides.
Criterion | Weight (1–5) | Rehost (rating 1–5) | Replatform (rating 1–5) | Repurchase (SaaS) (rating 1–5) | Refactor / re-architect (rating 1–5) | Guidance note
Time pressure | 4 | 5 | 4 | 3 | 1 | Datacenter exit dates favor rehost.
Cloud-native value | 4 | 1 | 3 | 4 | 5 | Elasticity, managed services, and velocity upside.
Application change risk | 5 | 5 | 4 | 2 | 1 | Fragile legacy apps punish refactoring.
SaaS fit | 3 | 1 | 1 | 5 | 1 | Commodity functions should be bought, not migrated.
Data gravity & coupling | 4 | 4 | 3 | 2 | 2 | Tightly coupled estates resist surgical moves.
Team cloud skill | 3 | 4 | 3 | 4 | 2 | Refactors need real cloud-native engineering.
License & cost impact | 4 | 3 | 4 | 5 | 4 | BYOL vs. SaaS vs. PaaS economics per app.
Strategic importance | 4 | 2 | 3 | 3 | 5 | Differentiating systems deserve refactor investment.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
Cloud Migration Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Discover & decide | Application inventory | Architect | 4–6 weeks | Complete inventory | Not started
| Dependency mapping | App owners + arch |  | Validated dependency map | Not started
| 6R dispositions | Architect + owners |  | Signed disposition register | Not started
| Business case per wave | Architect + finance |  | Wave-level TCO model | Not started
Phase 2 · Land | Landing zone build | Platform | 4–8 weeks | Reviewed landing zone | Not started
| Guardrails as code | Security |  | Enforced policies | Not started
| Connectivity | Network |  | Tested hybrid connectivity | Not started
| Shared services | Platform |  | CI/CD, monitoring, backup live | Not started
Phase 3 · Pilot wave | Migrate 2–3 low-risk apps | Migration team | 4–6 weeks | Pilot apps live in cloud | Not started
| Prove data migration | Data engineer |  | Lag within budget | Not started
| Cutover rehearsal | Program lead |  | Rehearsal timings | Not started
| Retrospective & plan update | Program lead |  | Updated wave plan | Not started
Phase 4 · Scale waves | Execute migration waves | Migration team | per wave 3–6 weeks | Apps live per wave plan | Not started
| Cutover + hypercare | App owners + ops |  | Green validation per wave | Not started
| Decommission source | Infra |  | Source infra retired per plan | Not started
| FinOps reviews | FinOps |  | Spend vs. model per wave | Not started
Phase 5 · Optimize & close | Rightsize & modernize | Platform | 4–6 weeks | Post-migration optimization backlog | Not started
| SRE adoption | Ops |  | SLOs + on-call for migrated estate | Not started
| Datacenter exit | Infra lead |  | Exit complete, savings realized | Not started
| Program retrospective | Program lead |  | Actuals, lessons, handover | Not started

## Validation Plan
Cloud Migration Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Landing zone | Guardrail efficacy | Attempt a policy violation in a sandbox account | Blocked automatically; alert fired | Pending
| Connectivity under load | Sustained throughput test | Meets design throughput with headroom | Pending
| Shared services | Deploy a test app end to end | CI/CD → deploy → monitor → backup works | Pending
Migration fidelity | Functional parity | App test suites in target | Pass rate equal to source environment | Pending
| Data parity | Reconcile migrated datasets | Match within tolerance; deltas explained | Pending
| Performance parity | Load test in target | p95 within 10% of source or better | Pending
Cutover | Rehearsal timing | Full cutover rehearsal | Completes within the signed window | Pending
| Rollback drill | Execute rollback in staging | Within time box; data consistent | Pending
| DNS/traffic flip | Verify traffic shift | 100% traffic on target; no split-brain | Pending
Security & compliance | Posture review | Scan migrated workloads | Meets baseline; findings remediated | Pending
| Access review | Verify IAM in target | Least-privilege; no standing admin | Pending
| Data residency | Verify data locations | Matches compliance mapping | Pending
Economics & closure | Cost vs. model | 30-day run-rate vs. wave model | Within 15% or explained | Pending
| Decommission verification | Source infra status | Decommissioned; contracts terminated | Pending
| Benefits realization | Exit savings + agility metrics | Reported to sponsors vs. business case | Pending