## README
AnovaCloud — Data Lake / Lakehouse Health Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Table-format / platform decision matrix
Score per candidate. The 'best' format is the one your team can operate and your ecosystem supports.
Criterion | Weight (1–5) | Delta Lake (rating 1–5) | Apache Iceberg (rating 1–5) | Apache Hudi (rating 1–5) | Managed lakehouse (rating 1–5) | Guidance note
Engine compatibility | 5 | 4 | 5 | 3 | 4 | Which engines must read/write (Spark, Flink, Trino, Snowflake, etc.)?
Team operating skill | 4 | 4 | 3 | 2 | 5 | Hudi/Iceberg need deeper table-maintenance expertise.
Streaming/upsert needs | 4 | 4 | 4 | 5 | 4 | Hudi leads on upsert-heavy streaming; Delta/Iceberg close behind.
Ecosystem & vendor fit | 4 | 5 | 4 | 3 | 5 | Databricks→Delta gravity; Snowflake/open→Iceberg gravity.
Governance features | 4 | 4 | 4 | 3 | 5 | Managed options bundle catalog/RBAC; open formats need add-ons.
Migration cost from current | 5 | 3 | 3 | 2 | 2 | In-place conversion vs. rewrite — price it.
Cost at scale | 3 | 4 | 4 | 4 | 3 | Open formats on object storage are cheapest; managed adds premium.
Community & longevity | 3 | 5 | 5 | 3 | 4 | Bet on formats with durable multi-vendor momentum.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
Data Lake / Lakehouse Health Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Assess | Inventory sources & pipelines | Data engineer | 2 weeks | Source/pipeline register | Not started
| Score the questionnaire | Architect |  | Scored risks | Not started
| Cost & trust baseline | FinOps + consumers |  | Cost attribution + trust survey | Not started
| Pick remediation scope | Leadership |  | Scoped wave 1 | Not started
Phase 2 · Stabilize ingestion | Fix top freshness failures | Data engineer | 3–4 weeks | SLA attainment ≥95% | Not started
| Idempotency & backfill safety | Data engineer |  | Safe re-run verified | Not started
| Schema-drift detection | Data engineer |  | Drift alerts live | Not started
| Kill or adopt shadow pipelines | Architect |  | One sanctioned path per source | Not started
Phase 3 · Curate the core | Enforce layer contracts | Analytics eng | 4–6 weeks | Contracts + violations blocked | Not started
| Rebuild top-5 gold datasets | Analytics eng |  | Trusted gold v2 | Not started
| DQ gates on critical paths | Data engineer |  | Gates live with alerts | Not started
| Catalog the gold layer | Governance |  | ≥90% catalogued | Not started
Phase 4 · Serve & optimize | Serving patterns per consumer | Architect | 3–4 weeks | Marts/caching/APIs in place | Not started
| Cost optimization pass | FinOps + eng |  | Top drivers reduced | Not started
| Compaction & lifecycle automation | Data engineer |  | Debt trending down | Not started
| Deprecate dead datasets | Governance |  | Deprecation log | Not started
Phase 5 · Operate | DQ & freshness reviews | Data engineer | ongoing | Weekly review log | Not started
| Consumer trust check-ins | Product |  | Quarterly trust survey | Not started
| Capacity planning | Architect |  | Growth plan | Not started
| Format/platform re-evaluation | Architect |  | Annual decision review | Not started

## Validation Plan
Data Lake / Lakehouse Health Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Freshness & reliability | SLA attainment | 30-day freshness SLA record | ≥95% attainment on critical pipelines | Pending
| Backfill safety | Re-run a full day's pipelines | Idempotent: no duplicates, correct results | Pending
| Schema-drift response | Introduce a source schema change in staging | Detected and handled per design; alert fired | Pending
Data quality | DQ gate efficacy | Inject bad data in staging | Gate blocks or quarantines; alert fires | Pending
| Reconciliation | Reconcile gold metrics to source systems | Match within tolerance on sampled metrics | Pending
| PII control test | Attempt unauthorized access to classified columns | Denied and logged | Pending
Performance | Top-query p95 | Top-10 consumer queries at typical concurrency | Within agreed p95 targets | Pending
| File health | File-size distribution on hot tables | No small-file crisis; compaction keeping up | Pending
| Concurrency | Burst test on serving layer | No query failures at 2x typical load | Pending
Lineage & change | Lineage trace | Trace 3 gold metrics to bronze | Complete trace in <15 minutes each | Pending
| Breaking-change drill | Propose a gold schema change | Versioned, announced, consumers migrated | Pending
| Time-travel restore | Restore a table to a prior version | Completes within RTO; data verified | Pending
Cost | Attribution accuracy | Verify cost allocation vs. actuals | Allocated ≥95% of spend to owners | Pending
| Optimization delta | Re-measure top cost drivers | Documented reduction or justified spend | Pending
| Storage growth | Growth rate vs. plan | Within plan; lifecycle policies effective | Pending