## README
AnovaCloud — Databricks Engineering Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Databricks platform decision matrix
Score the big platform calls. These decisions are expensive to revisit — make them deliberately.
Criterion | Weight (1–5) | Optimize current estate (rating 1–5) | Unity Catalog migration (rating 1–5) | Medallion rebuild (rating 1–5) | Re-platform off Databricks (rating 1–5) | Guidance note
Governance urgency | 5 | 2 | 5 | 4 | 3 | Audit/compliance pressure forces Unity Catalog or rebuild.
Performance headroom | 4 | 4 | 3 | 5 | 2 | Deep perf problems may need rebuild, not tuning.
Migration/disruption cost | 5 | 5 | 3 | 1 | 1 | Rebuilds and re-platforms are multi-quarter programs.
Team skill | 3 | 4 | 3 | 3 | 2 | Score the team you have.
Ecosystem lock-in tolerance | 3 | 3 | 3 | 3 | 5 | Only re-platform if lock-in is the actual problem.
Cost trajectory | 4 | 4 | 3 | 4 | 3 | Will this bend the DBU curve? Model it.
ML/AI roadmap fit | 4 | 4 | 4 | 5 | 2 | Feature store, MLflow, agent workloads favor staying.
Time to value | 4 | 5 | 3 | 2 | 1 | Optimize pays this quarter; rebuilds pay next year.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
Databricks Engineering Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Assess | Workspace & UC audit | Platform admin | 2 weeks | Governance gap report | Not started
| DBU & workload analysis | FinOps + eng |  | Top-consumer list | Not started
| Score the questionnaire | Architect |  | Scored risks | Not started
| Decide platform direction | Leadership |  | Matrix decision, written | Not started
Phase 2 · Govern | Unity Catalog migration wave 1 | Platform | 3–4 weeks | Critical data governed | Not started
| Cluster policies & tagging | Platform |  | 100% compliance | Not started
| Service-principal cutover | Security + platform |  | No PATs in prod | Not started
| PII classification sprint | Governance |  | Sensitive data classified | Not started
Phase 3 · Perform | Maintenance automation | Data engineer | 4–6 weeks | OPTIMIZE/VACUUM scheduled | Not started
| Top-10 job tuning | Data engineer |  | Measured runtime reductions | Not started
| Delta expectations rollout | Data engineer |  | Write-time DQ live | Not started
| Workflows hardening | Data engineer |  | SLAs + CI/CD on top pipelines | Not started
Phase 4 · FinOps | Attribution & alerts | FinOps | 3 weeks | Dashboards + anomaly alerts | Not started
| Top-consumer optimization | Owners |  | Backlog with owners | Not started
| Idle-resource purge | Platform |  | Zombie cleanup log | Not started
| Commitment decision | Leadership |  | Commit/don't-commit, modeled | Not started
Phase 5 · Operate | Monthly perf & cost review | Platform + FinOps | ongoing | Review log | Not started
| Quarterly governance audit | Governance |  | Audit findings | Not started
| Runbook drills | Ops |  | Drill records | Not started
| Roadmap check (serverless/AI) | Architect |  | Annual platform review | Not started

## Validation Plan
Databricks Engineering Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Performance | Top-job runtime delta | Re-run top-10 jobs post-tuning | ≥20% improvement or documented constraint | Pending
| Maintenance effectiveness | File metrics on hot tables | Compaction keeping up; no small-file growth | Pending
| Skew/spill elimination | Spark UI on treated jobs | No pathological skew/spill on top jobs | Pending
Reliability | Failed-run rate | 30-day workflow history | Trending down; top causes have fixes | Pending
| SLA attainment | Pipeline SLA record | ≥95% on critical pipelines | Pending
| CI/CD compliance | Audit prod job definitions | 100% deployed via pipeline, zero manual edits | Pending
Governance | Grant audit | Re-sample grants quarterly | Zero excessive grants on sensitive data | Pending
| Policy compliance | Cluster policy compliance | ≥95% compliant clusters | Pending
| Lineage completeness | Trace 3 critical datasets | End-to-end lineage in Unity Catalog | Pending
Cost | DBU per run | Top-10 jobs, before/after | Down or justified; no unexplained growth | Pending
| Attribution coverage | Spend allocated to owners | ≥95% attributed | Pending
| Anomaly detection | Inject a spend spike in dev | Alert fires within the agreed window | Pending
Security & DR | Masking verification | Query masked data as restricted role | Masking/row-filters enforced | Pending
| Credential hygiene | Scan for PATs in prod | Zero personal tokens in production | Pending
| DR drill | Recover a critical Delta table | Within RTO; data verified | Pending