## README
AnovaCloud — Enterprise RAG Build Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
RAG stack decision matrix
Score 1–5 per option. Weight reflects enterprise reality: security and eval-readiness dominate.
Criterion | Weight (1–5) | Managed search + LLM (rating 1–5) | Open-source stack (rating 1–5) | Vendor RAG platform (rating 1–5) | Defer / fix corpus first (rating 1–5) | Guidance note
Time to pilot | 3 | 5 | 2 | 4 | 1 | Managed and vendor options pilot fastest.
Data control & residency | 5 | 3 | 5 | 2 | 5 | Regulated data favors self-hosted open source.
Retrieval tunability | 4 | 3 | 5 | 2 | 1 | Chunking, hybrid, rerank control is deepest in open source.
Eval & observability | 4 | 3 | 4 | 4 | 1 | You still need your own golden set everywhere.
Total cost at scale | 4 | 3 | 4 | 2 | 5 | Model per-query cost dominates at scale; model it.
Team skill fit | 4 | 4 | 2 | 4 | 1 | Open source needs search/ML-ops depth.
Vendor lock-in risk | 3 | 2 | 5 | 1 | 5 | Embeddings and chunking choices create switching costs.
Compliance posture | 5 | 3 | 5 | 3 | 5 | Audit, logging, and DPA requirements per option.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
Enterprise RAG Build Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Corpus & questions | Inventory sources & owners | Knowledge lead | 2–3 weeks | Source inventory | Not started
| Collect 50+ real user questions | Product |  | Question sample | Not started
| Build golden Q/A set | Domain experts |  | Golden set v1 | Not started
| Corpus quality audit | Knowledge lead |  | Dedup/staleness report | Not started
Phase 2 · Retrieval baseline | Stand up ingestion pipeline | Data engineer | 3–4 weeks | Incremental ingestion working | Not started
| Chunking experiments | ML engineer |  | Chosen chunking + recall@k | Not started
| Baseline hybrid retrieval | ML engineer |  | recall@k baseline on golden set | Not started
| ACL pre-filter design | Security + eng |  | Access-control architecture | Not started
Phase 3 · Generation & eval | Generation with citations | ML engineer | 3–4 weeks | Cited answers on golden set | Not started
| Faithfulness eval harness | ML engineer |  | Automated grounding metrics | Not started
| Refusal & injection tests | Security |  | Adversarial test results | Not started
| Human review loop | Domain experts |  | Grading rubric + cadence | Not started
Phase 4 · Pilot | Internal pilot launch | Product | 4–6 weeks | Pilot cohort live | Not started
| SLO dashboards & alerts | Platform |  | Latency/freshness/cost dashboards | Not started
| Feedback-to-fix loop | Product + eng |  | Weekly triage operating | Not started
| Gate review | Architect + owner |  | Written expand/hold decision | Not started
Phase 5 · Harden & expand | Expand sources & audience | Knowledge + product | ongoing | Rollout waves | Not started
| Continuous eval | ML engineer |  | Eval on fresh questions monthly | Not started
| Cost optimization | Engineering |  | Cost per query trending down | Not started
| Corpus governance cadence | Knowledge lead |  | Quarterly corpus review | Not started

## Validation Plan
Enterprise RAG Build Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Retrieval quality | recall@k on golden set | Automated retrieval eval | recall@10 ≥ agreed threshold (e.g., 0.85) | Pending
| Exact-match queries | ID/code/name lookup questions | 100% retrieve the correct document | Pending
| Freshness propagation | Update a source doc, re-query | Updated content retrievable within freshness SLA | Pending
Grounding | Faithfulness rate | Claim-level check vs. retrieved chunks | ≥95% of claims supported by citations | Pending
| Citation accuracy | Verify citations point to supporting text | ≥95% citation precision | Pending
| Refusal behavior | Out-of-corpus questions | Refuses or hedges per spec; zero confident fabrications | Pending
Security | ACL enforcement | Query as users with different permissions | Zero documents visible beyond each user's access | Pending
| Permission-change lag | Revoke access, re-query | Revocation effective within agreed window | Pending
| Injection resistance | Planted malicious instructions in docs | System ignores injected instructions 100% | Pending
Performance & cost | Latency SLO | p95 end-to-end on golden set at pilot concurrency | Within SLO | Pending
| Cost per 1k queries | Measure at pilot load | Within budget; 10x projection modeled | Pending
| Availability | SLO window measurement | Meets target (e.g., 99.5%) | Pending
Operations | Index rebuild/rollback | Rebuild index; roll back a bad version | Completes within maintenance window | Pending
| Feedback loop | Submit feedback, verify triage | Feedback reaches an owner within SLA | Pending
| Audit completeness | Sample logged interactions | 100% have prompt, chunks, answer, and user identity | Pending