## README
AnovaCloud — PostgreSQL Health & Performance Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Remediation path decision matrix
Score each cluster 1–5 per criterion per option. The highest weighted total is the default recommendation — override it only with a written reason.
Criterion | Weight (1–5) | Tune in place (rating 1–5) | Major version upgrade (rating 1–5) | Re-architect (replicas/sharding) (rating 1–5) | Move to managed service (rating 1–5) | Guidance note
Version currency | 4 | 3 | 5 | 3 | 5 | Two+ majors behind pushes toward upgrade or managed.
Query/index fixability | 5 | 5 | 4 | 3 | 4 | If top queries are fixable, tuning wins fast.
Scale headroom needed | 4 | 2 | 3 | 5 | 4 | 10x growth favors re-architecture or managed elasticity.
Team operating skill | 4 | 3 | 2 | 1 | 5 | Low Postgres ops maturity strongly favors managed.
Downtime/change budget | 3 | 5 | 3 | 2 | 3 | Tight windows favor in-place tuning.
Compliance/control needs | 3 | 4 | 4 | 4 | 3 | Strict data-residency or custom controls can disfavor managed.
Cost sensitivity | 3 | 5 | 4 | 2 | 3 | Managed trades license-like fees for ops labor.
Extension/customization load | 3 | 4 | 3 | 3 | 2 | Heavy custom extensions complicate managed moves.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
PostgreSQL Health & Performance Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Baseline | Enable pg_stat_statements & baselines | DBA | 1 week | Baseline metrics pack | Not started
| Run bloat, lag, config scans | DBA |  | Scan reports | Not started
| Rank top-20 queries by total time | DBA + dev |  | Top-query list | Not started
| Score the questionnaire | Architect |  | Scored risks | Not started
Phase 2 · Diagnose | EXPLAIN ANALYZE top offenders | DBA + dev | 2 weeks | Per-query findings | Not started
| Lock/wait-event analysis | DBA |  | Contention report | Not started
| Config vs. workload review | DBA |  | Config change proposals | Not started
| Backup/restore & failover drill | Ops |  | Drill timings | Not started
Phase 3 · Remediate | Ship index & query fixes | Dev + DBA | 3–4 weeks | Fixed queries, measured delta | Not started
| Tune autovacuum & memory | DBA |  | New config, rollout plan | Not started
| Fix connection pooling | Platform |  | Pooler in path, churn reduced | Not started
| Address bloat (VACUUM/repack) | DBA |  | Bloat reclaimed, trend flat | Not started
Phase 4 · Harden | Dashboards & alerts | Ops | 2 weeks | Live dashboards, alert rules | Not started
| Runbooks for top incidents | DBA + ops |  | Published runbooks | Not started
| Backup/PITR automation | Ops |  | Scheduled, monitored backups | Not started
| Security hardening pass | DBA + security |  | Hardening checklist signed | Not started
Phase 5 · Sustain | Weekly slow-query review | DBA | ongoing | Review log | Not started
| Monthly bloat & growth review | DBA |  | Capacity report | Not started
| Quarterly failover drill | Ops |  | Drill record | Not started
| Version upgrade planning | Architect |  | Upgrade runway plan | Not started

## Validation Plan
PostgreSQL Health & Performance Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Query performance | Top-query latency delta | Re-run top-20 queries, compare p95 to baseline | p95 improved or stable; no regressions >10% | Pending
| Sequential-scan reduction | Count seq scans on large tables in top queries | Zero avoidable seq scans in top-20 | Pending
| Concurrency test | Replay peak concurrency against fixed queries | Throughput meets peak with p99 within SLO | Pending
Storage health | Bloat re-measurement | Re-run bloat estimates on treated tables | Bloat <10% on treated tables, trend flat 14 days | Pending
| Autovacuum keeping up | Dead-tuple trend over 7 days post-change | n_dead_tup bounded, no manual VACUUM needed | Pending
| Checkpoint smoothness | I/O graph during checkpoints | No checkpoint-driven latency spikes | Pending
Resilience | PITR restore drill | Restore to a chosen point in time | RTO/RPO met, data verified | Pending
| Failover drill | Promote replica under production-like load | Failover within RTO, zero lost writes beyond RPO | Pending
| Backup integrity | Restore latest backup to scratch | Restore succeeds, checksums verify | Pending
Connections & load | Connection churn | Measure connections/sec on primary | Churn reduced ≥50% vs. baseline via pooling | Pending
| Pool saturation | Pooler wait-queue metrics at peak | Zero client-visible pool timeouts at peak | Pending
| Lock contention | Wait-event sampling at peak | No chronic lock waits on hot paths | Pending
Observability | Alert efficacy | Induce a fault in staging | Correct alert fires within 5 minutes | Pending
| Dashboard completeness | Review against metric list | All checklist metrics visible on dashboards | Pending
| Runbook drill | On-call follows runbook for simulated incident | Incident resolved per runbook without escalation | Pending