## README
AnovaCloud — Snowflake Optimization Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Snowflake strategy decision matrix
Score per account/workload group. Most estates need 'rightsize + remodel', not a platform change.
Criterion | Weight (1–5) | Rightsize & tune (rating 1–5) | Remodel (dbt/marts) (rating 1–5) | Full FinOps program (rating 1–5) | Re-platform (rating 1–5) | Guidance note
Waste share of spend | 5 | 5 | 3 | 5 | 2 | High idle/oversize waste → tune + FinOps win fast.
Modeling debt | 5 | 2 | 5 | 3 | 2 | Deep modeling debt needs the remodel, not warehouse tweaks.
Performance pain | 4 | 4 | 5 | 2 | 2 | Slow dashboards usually trace to modeling + sizing.
Org cost accountability | 4 | 3 | 2 | 5 | 2 | No accountability → FinOps program is the fix.
Disruption tolerance | 4 | 5 | 3 | 4 | 1 | Remodels touch every dashboard; plan the comms.
Team analytics-eng skill | 3 | 4 | 3 | 3 | 2 | Remodels need real analytics engineering.
Contract/commit position | 3 | 4 | 4 | 4 | 1 | Commits change the math; re-platforms waste them.
Time to savings | 4 | 5 | 3 | 4 | 1 | Tuning pays in weeks; remodels in quarters.
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
Snowflake Optimization Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Assess | Top-consumer analysis | FinOps + admin | 2 weeks | Top-10 credit consumers | Not started
| Warehouse audit | Admin |  | Inventory + sizing findings | Not started
| Score the questionnaire | Architect |  | Scored risks | Not started
| Strategy decision | Leadership |  | Matrix decision, written | Not started
Phase 2 · Stop the waste | Right-size warehouses | Admin | 2–3 weeks | New sizes + measured savings | Not started
| Auto-suspend tuning | Admin |  | Idle burn ≈ 0 | Not started
| Resource monitors | Admin |  | Monitors with actions live | Not started
| Query tagging standard | Analytics eng |  | ≥95% tagged | Not started
Phase 3 · Remodel hot paths | Clustering keys | Analytics eng | 4–6 weeks | Pruning verified | Not started
| Gold marts for top dashboards | Analytics eng |  | Marts live, dashboards cut over | Not started
| Top-20 query tuning | Analytics eng |  | p95 improvements measured | Not started
| Pre-aggregation | Analytics eng |  | Wasteful recompute eliminated | Not started
Phase 4 · FinOps | Attribution & budgets | FinOps | 3 weeks | Per-team budgets + alerts | Not started
| Showback cadence | FinOps |  | Monthly showback operating | Not started
| Storage optimization | Admin |  | Retention right-sized | Not started
| Commit evaluation | Leadership |  | Commit decision, modeled | Not started
Phase 5 · Operate | Monthly cost & perf review | FinOps + eng | ongoing | Review log | Not started
| Quarterly model review | Analytics eng |  | Model health check | Not started
| Anomaly drills | Ops |  | Drill records | Not started
| Annual strategy review | Architect |  | Platform decision revisited | Not started

## Validation Plan
Snowflake Optimization Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Cost | Credit delta | Compare 30-day credit burn before/after | Documented reduction; no unexplained growth | Pending
| Idle share | Idle credits / total | <5% and falling | Pending
| Attribution coverage | Credits with valid tags | ≥95% attributable to team/purpose | Pending
Performance | Dashboard p95 | Top-10 dashboards before/after | p95 stable or improved; zero regressions | Pending
| Query pruning | Large-table selective queries | Partition/cluster pruning confirmed | Pending
| Concurrency | Peak-period queuing | Zero user-visible queuing at normal peaks | Pending
Modeling | Mart adoption | Top dashboards' data sources | 100% on modeled marts, not raw tables | Pending
| Cache hit rate | Result cache on top dashboards | Improved or deliberately bypassed with reason | Pending
| dbt test pass | dbt test suite | 100% pass in CI; documented exceptions | Pending
Governance | RBAC re-audit | Sample roles quarterly | Least-privilege maintained | Pending
| Masking verification | Adversarial queries as restricted roles | PII masked; access logged | Pending
| Share review | Outbound shares | All approved; stale shares revoked | Pending
Operations | Monitor efficacy | Induce a cost spike in dev | Resource monitor alerts/fires per policy | Pending
| Incident drill | Simulate perf incident | Runbook followed; comms sent | Pending
| Retention compliance | Storage retention settings | Match policy; no surprise Failsafe bills | Pending