## README
AnovaCloud — SQL Server → PostgreSQL Migration Pack
This workbook is the working companion to the pack's questionnaire and checklist PDFs.
Sheet 1 · Decision Matrix — score each option 1–5 per criterion. Weighted totals compute automatically. The winner is the default recommendation; override it only with a written reason in the notes column.
Sheet 2 · Project Plan — phases, tasks, owners, and deliverables. Set entry/exit criteria per phase; no phase starts until the prior phase's validation rows are green.
Sheet 3 · Validation Plan — the test plan. Record Result (Pass/Fail/Pending) and evidence for every row. Nothing ships with a red row.
Scoring scale: 1 = weak / high risk, 5 = strong / low risk. Score from evidence, not optimism.
© 2026 AnovaCloud — anovacloud.com · Frisco, Texas

## Decision Matrix
Workload disposition decision matrix
Score each significant database 1–5 per criterion, multiply by weight, and compare weighted totals across dispositions. The matrix does not decide for you — it forces the trade-offs into the open.
Criterion | Weight (1–5) | Migrate to PostgreSQL (rating 1–5) | Rehost SQL Server (managed) (rating 1–5) | Refactor to cloud-native (rating 1–5) | Retain on-prem (rating 1–5) | Guidance note
License cost avoidance | 5 | 5 | 2 | 4 | 1 | PostgreSQL eliminates license cost; rehost/retain keep paying.
T-SQL conversion complexity | 4 | 2 | 5 | 2 | 5 | Heavy T-SQL/CLR favors staying on SQL Server.
Downtime tolerance | 4 | 3 | 4 | 2 | 5 | Near-zero-downtime favors rehost or retain; migration needs CDC maturity.
Team PostgreSQL skill | 3 | 2 | 4 | 2 | 5 | Score current team capability, not the hiring plan.
HA/DR parity achievable | 4 | 4 | 5 | 4 | 5 | Can the target meet the workload's RPO/RTO?
Ecosystem fit (extensions, tooling) | 3 | 5 | 3 | 4 | 3 | Postgres extension ecosystem vs. SQL Server tooling lock-in.
Timeline pressure | 3 | 2 | 5 | 1 | 5 | Tight deadlines favor rehost/retain; migration is a program, not a task.
Strategic platform direction | 4 | 5 | 2 | 5 | 1 | Does the enterprise standard point at open source / cloud-native?
WEIGHTED TOTAL | [5 empty] | Highest total = recommended default

## Project Plan
SQL Server → PostgreSQL Migration Pack — project plan
Phase | Task | Owner | Duration | Deliverable | Status | Notes
Phase 1 · Assess | Run estate & feature scans | DBA lead | 2–3 weeks | Scanned inventory per database | Not started
| Complete discovery questionnaire | Architect |  | Scored questionnaire with risks | Not started
| Build 3-year TCO model | Architect + Finance |  | Stay-vs-migrate economics | Not started
| Draft wave plan | Program lead |  | Sequenced waves with entry criteria | Not started
Phase 2 · Convert & prove | Pilot schema conversion (1 workload) | Migration engineer | 4–6 weeks | Converted schema + remediation backlog | Not started
| Build data-validation harness | QA / data engineer |  | Automated parity checks | Not started
| Remediate application code | App teams |  | App code passing against PostgreSQL | Not started
| Design target HA/DR & backup | DBA lead |  | Target operations architecture | Not started
Phase 3 · Migrate & sync | Execute full load (non-prod first) | Migration engineer | 3–5 weeks per wave | Loaded target, validated | Not started
| Establish CDC replication | DBA lead |  | Replication within lag SLO | Not started
| Dual-run application traffic (shadow) | App teams |  | Shadow results, zero customer impact | Not started
| Performance test at peak load | Performance engineer |  | Signed performance report | Not started
Phase 4 · Cutover | Cutover rehearsal | Program lead | 1–2 weeks per wave | Rehearsal timings + issues log | Not started
| Execute go/no-go gate | Accountable owner |  | Signed go/no-go record | Not started
| Flip connections, final sync | DBA + app leads |  | Production on PostgreSQL | Not started
| Hypercare (72h watch) | DBA lead |  | Hypercare log, zero sev-1 | Not started
Phase 5 · Harden & optimize | Tune vacuum, indexes, queries | DBA lead | 2–4 weeks | Tuning backlog closed | Not started
| Finalize runbooks & monitoring | Ops |  | Live runbooks | Not started
| Decommission SQL Server | Infra lead |  | Decommissioned, licenses trued down | Not started
| Program retrospective | Program lead |  | Lessons + cost actuals vs. model | Not started

## Validation Plan
SQL Server → PostgreSQL Migration Pack — validation plan
Record Result and evidence for every row. Nothing ships with a red (Fail) row.
Category | Test | Method | Pass criteria | Result | Evidence / notes | Date
Schema parity | Object inventory match | Automated diff of converted schema vs. source inventory | 100% of in-scope objects converted or explicitly dispositioned | Pending
| Constraint & index parity | Compare constraints, indexes, defaults per table | Zero missing constraints/indexes on migrated tables | Pending
| Data-type mapping review | Sample-based review of mapped types | All risky mappings (datetime, numeric, text) signed off | Pending
Data parity | Row counts per table | Automated count comparison post-load | Exact match on all tables, or explained deltas | Pending
| Checksum comparison | Hash-based comparison on large tables | Checksums match within the agreed tolerance window | Pending
| Business-key spot checks | Analyst-written spot queries on critical entities | All spot queries return expected results | Pending
Performance | Top-query regression test | Replay top-50 production queries at peak concurrency | p95 latency within 10% of SQL Server baseline or better | Pending
| Write throughput test | Sustained insert/update load test | Meets documented peak TPS with headroom ≥20% | Pending
| Vacuum/autovacuum behavior | Observe under sustained write load | No bloat-driven degradation over 72h | Pending
Functional | Application smoke suite | App team's smoke tests against PostgreSQL | 100% pass before cutover | Pending
| Batch & job parity | Run ETL/batch jobs end to end | Outputs byte-identical or approved-different | Pending
| Rollback drill | Execute rollback in staging | Rollback completes within the downtime budget | Pending
Operational | Backup & PITR restore | Restore from backup to a point in time | RTO/RPO met in a timed drill | Pending
| Failover drill | Promote replica under load | Failover within RTO, app reconnects automatically | Pending
| Monitoring coverage | Verify alerts fire on induced faults | All sev-1 scenarios alert within 5 minutes | Pending